## Questions
Team Questions
Project |  | Points and Holding ADSS |  |  | Project # | N/A
Project Manager |  | Sharon Hall |  |  | Sponsor | FAA
Project artifacts location |  | TBD |  |  | Updated | 2014-06-17
ID | Question(s) | Owner | Status | Date Entered | Planned Completion | Actual Completion | Origin/ Response
1 | When will we get access or connectivity to FAA systems | Jeff G. | Open | 2014-06-17 | 2014-06-20 |  | Program Req Document (PRD)
2 | What continuous build tools are FAA currently using? e.g Eclipse | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
3 | What configuration management tools are currently being used? | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
4 | Can we talk to the technical POC for the Gov't? | Jeff G. | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
5 | Where do we locate the NavLean Data Strategic Initiative? | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
6 | Where do we get detailed information on AIXM? | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
7 | Where can we locate/access the 8260-2 Form? | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
8 | What is the process for identifying wayward points? | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
9 | What system is used for Authentication? e.g. Oracle Access Manager | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
10 | How do we obtain the SWIM framework? | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
11 | How are the external systems currently talking to IFP FIX? | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
12 | Will the legacy systems be decommissioned? Is this an opportunity? | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
13 | What are FAA's 508 Compliance Standards? Verification and Validation. | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
14 | Do we have to write a Transition Plan? | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
15 | What are the current development platforms? | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
16 | Is Cloud computing capability a valid requirement at this time? | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
17 | What are the requirements for single sign on (SSO)? | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
18 | Need clarification on section 3.1.1.1 - Area of responsibility | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
19 | Need clarification on section 3.1.2.3 - FICAM | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
20 | Need access to Solution Design | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
21 | What is procedural data | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
22 | What is form metadata | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
22 | Need clarification on section 3.4.1.3 - RADIALS | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
22 | Need clarification on section 3.4.1.6 - Chart Publication | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
22 | Is it possible to arrange a tour of the customer facility? | Jeff G. | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
22 | Need clarification on section 3.2.5.10 - Manual and Terrain Obstacles | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
22 | Need clarification on section 3.2.6.0 - NAS Data Changes (NFDD Report) | Gov't POC | Open | 2014-06-17 | 2014-06-26 |  | Program Req Document (PRD)
22
22
Note on D6: Options are: Open Closed